## Checklist
Conference planning checklist
Event name |  |  | Overdue
Event date |  |  | Done
Date to check against |  |  | Done (%)
Amber window (days) | 7 |  | Weeks before: a negative number means after the event. Red: overdue. Amber: due within the window.
Area | Task | Weeks before | Due date | Owner | Status | Notes
Speakers & call for papers | Define the themes and tracks | 40 |  |  | Not started
Speakers & call for papers | Open the call for papers | 36 |  |  | Not started
Speakers & call for papers | Close the call and select the talks | 28 |  |  | Not started
Speakers & call for papers | Notify speakers and collect their bios | 24 |  |  | Not started
Speakers & call for papers | Collect slides and AV needs from speakers | 3 |  |  | Not started
Program & rooms | Draft the schedule across rooms | 20 |  |  | Not started
Program & rooms | Match sessions to rooms by expected audience | 16 |  |  | Not started
Program & rooms | Plan breaks, meals and networking time | 12 |  |  | Not started
Program & rooms | Publish the program | 10 |  |  | Not started
Registration | Set ticket types and open registration | 26 |  |  | Not started
Registration | Send reminders to past attendees | 16 |  |  | Not started
Registration | Set up the check-in process | 6 |  |  | Not started
Registration | Prepare the final attendee list | 1 |  |  | Not started
Sponsors & exhibitors | Define the sponsor packages | 36 |  |  | Not started
Sponsors & exhibitors | Approach sponsors and exhibitors | 30 |  |  | Not started
Sponsors & exhibitors | Sign sponsor agreements | 20 |  |  | Not started
Sponsors & exhibitors | Send the exhibitor manual | 12 |  |  | Not started
Sponsors & exhibitors | Confirm the booth layout | 6 |  |  | Not started
Venue & hotels | Choose and contract the venue | 44 |  |  | Not started
Venue & hotels | Block hotel rooms | 30 |  |  | Not started
Venue & hotels | Share the hotel booking link with attendees | 20 |  |  | Not started
AV per room | List the AV needs of each room | 14 |  |  | Not started
AV per room | Order equipment and confirm the technical crew | 10 |  |  | Not started
AV per room | Plan a tech check in each room | 2 |  |  | Not started
AV per room | Set up a speaker ready room | 1 |  |  | Not started
Badges & app | Choose a conference app or schedule page | 14 |  |  | Not started
Badges & app | Design and order the badges | 6 |  |  | Not started
Badges & app | Print badges and sort them for check-in | 2 |  |  | Not started
Accessibility | Check accessible routes and rooms | 16 |  |  | Not started
Accessibility | Ask attendees about access needs at registration | 14 |  |  | Not started
Accessibility | Arrange captioning or interpretation where needed | 8 |  |  | Not started
Accessibility | Plan a quiet space | 6 |  |  | Not started
Communications | Launch the conference website | 30 |  |  | Not started
Communications | Announce speakers to promote the event | 20 |  |  | Not started
Communications | Send the attendee practical guide | 2 |  |  | Not started
Event days | Brief volunteers and staff | 0 |  |  | Not started
Event days | Brief the session chairs | 0 |  |  | Not started
Event days | Keep each room on time | 0 |  |  | Not started
Event days | Tear down and return rented items | 0 |  |  | Not started
After the conference | Send the attendee survey | -1 |  |  | Not started
After the conference | Thank speakers and sponsors | -1 |  |  | Not started
After the conference | Share slides and recordings | -2 |  |  | Not started
After the conference | Hold a team debrief | -3 |  |  | Not started
After the conference | Report results to sponsors | -4 |  |  | Not started

## By area
By area
Area | Tasks | Done | Overdue | % done
Speakers & call for papers
Program & rooms
Registration
Sponsors & exhibitors
Venue & hotels
AV per room
Badges & app
Accessibility
Communications
Event days
After the conference
Other
Total

## How to use
How to use
This checklist walks through the tasks of a conference with several sessions and speakers, by how many weeks before the event each one is due.
Checklist tab: fill in the event name and the event date. Each task has a number of weeks before the event, and its due date is calculated: the event date minus that many weeks.
Weeks before accepts a whole number from -52 to 104. A negative number means after the event (-2 is two weeks after). Weeks before 0 is the event date. Leave it empty and the due date stays empty.
The tasks and their timing are an example to adapt, not a standard: change the tasks, the owners and the weeks to fit your event.
Date to check against starts as today (=TODAY()). Type a date over it to see where you will stand on another day.
Pick the Status from the list: Not started, In progress, Done or N/A. A task marked N/A is left out of the counts.
A row turns red when its due date has passed and its status is neither Done nor N/A. It turns amber when the due date falls within the amber window (7 days by default, change it in the Amber window cell). A task marked Done or N/A turns neither red nor amber.
Counters at the top: overdue tasks, done tasks, and the share done. The By area tab shows the same counts for each area. Tasks with an area of your own are counted under Other.
Enter dates as real dates (Oct 20, 2026). Use the empty rows at the bottom to add tasks: for more, copy a whole row, formula included, and insert it above the last row of the table, so the counts and colors follow.
The article that walks through the method: https://squena.com/blog/conference-planning-checklist?utm_source=modele-xlsx&utm_medium=fichier&utm_campaign=conference-planning-checklist
Template by Squena, the workspace for event organizers — squena.com