## Checklist
Corporate event planning checklist
Event name |  |  | Overdue
Event date |  |  | Done
Date to check against |  |  | Done (%)
Amber window (days) | 7 |  | Weeks before: a negative number means after the event. Red: overdue. Amber: due within the window.
Area | Task | Weeks before | Due date | Owner | Status | Notes
Budget & approvals | Confirm the purpose of the event and how you will judge success | 24 |  |  | Not started
Budget & approvals | Get the budget approved by the sponsor | 22 |  |  | Not started
Budget & approvals | Agree who signs contracts and approves spending | 22 |  |  | Not started
Budget & approvals | Set aside a contingency line in the budget | 20 |  |  | Not started
Venue | Shortlist venues and visit the best ones | 20 |  |  | Not started
Venue | Sign the venue contract | 16 |  |  | Not started
Venue | Confirm the floor plan and capacity | 8 |  |  | Not started
Vendors | Request quotes for catering, AV and decor | 16 |  |  | Not started
Vendors | Compare quotes and choose vendors | 14 |  |  | Not started
Vendors | Sign vendor contracts | 12 |  |  | Not started
Vendors | Confirm each vendor's arrival time and on-site contact | 1 |  |  | Not started
Program | Draft the agenda and the format | 14 |  |  | Not started
Program | Confirm speakers and hosts | 10 |  |  | Not started
Program | Finalize the run of show | 2 |  |  | Not started
Invitations & RSVPs | Build the guest list | 12 |  |  | Not started
Invitations & RSVPs | Send a save-the-date | 10 |  |  | Not started
Invitations & RSVPs | Send the invitations | 8 |  |  | Not started
Invitations & RSVPs | Collect dietary and accessibility needs | 5 |  |  | Not started
Invitations & RSVPs | Follow up on missing replies | 4 |  |  | Not started
Invitations & RSVPs | Close RSVPs and share final numbers with vendors | 2 |  |  | Not started
Travel & lodging | Block hotel rooms for out-of-town guests | 14 |  |  | Not started
Travel & lodging | Share travel and arrival instructions | 6 |  |  | Not started
Policies & duty of care | Check company rules on spending, gifts and alcohol | 16 |  |  | Not started
Policies & duty of care | Review safety and emergency plans with the venue | 6 |  |  | Not started
Policies & duty of care | Brief staff on conduct and their roles | 3 |  |  | Not started
Policies & duty of care | Set up a way to reach guests in an emergency | 2 |  |  | Not started
Communications | Brief internal communications | 10 |  |  | Not started
Communications | Prepare signage and printed materials | 4 |  |  | Not started
Communications | Send the final practical details to guests | 1 |  |  | Not started
Event day | Set up and test the equipment | 0 |  |  | Not started
Event day | Hold a team briefing before doors open | 0 |  |  | Not started
Event day | Run registration and welcome | 0 |  |  | Not started
Event day | Tear down and return rented items | 0 |  |  | Not started
Follow-up | Thank guests, speakers and vendors | -1 |  |  | Not started
Follow-up | Send a satisfaction survey | -1 |  |  | Not started
Follow-up | Hold a team debrief | -2 |  |  | Not started
Follow-up | Pay the remaining vendor invoices | -2 |  |  | Not started
Follow-up | Report results against the goals | -3 |  |  | Not started

## By area
By area
Area | Tasks | Done | Overdue | % done
Budget & approvals
Venue
Vendors
Program
Invitations & RSVPs
Travel & lodging
Policies & duty of care
Communications
Event day
Follow-up
Other
Total

## How to use
How to use
This checklist walks through the tasks of a corporate event (seminar, party, launch, annual meeting), by how many weeks before the event each one is due.
Checklist tab: fill in the event name and the event date. Each task has a number of weeks before the event, and its due date is calculated: the event date minus that many weeks.
Weeks before accepts a whole number from -52 to 104. A negative number means after the event (-2 is two weeks after). Weeks before 0 is the event date. Leave it empty and the due date stays empty.
The tasks and their timing are an example to adapt, not a standard: change the tasks, the owners and the weeks to fit your event.
Date to check against starts as today (=TODAY()). Type a date over it to see where you will stand on another day.
Pick the Status from the list: Not started, In progress, Done or N/A. A task marked N/A is left out of the counts.
A row turns red when its due date has passed and its status is neither Done nor N/A. It turns amber when the due date falls within the amber window (7 days by default, change it in the Amber window cell). A task marked Done or N/A turns neither red nor amber.
Counters at the top: overdue tasks, done tasks, and the share done. The By area tab shows the same counts for each area. Tasks with an area of your own are counted under Other.
Enter dates as real dates (Oct 20, 2026). Use the empty rows at the bottom to add tasks: for more, copy a whole row, formula included, and insert it above the last row of the table, so the counts and colors follow.
The article that walks through the method: https://squena.com/blog/corporate-event-planning-checklist?utm_source=modele-xlsx&utm_medium=fichier&utm_campaign=corporate-event-planning-checklist
Template by Squena, the workspace for event organizers — squena.com