## Day-of schedule
Day-of event schedule
Event name
Date
Venue
Venue address
Day-of lead (name, phone)
Venue contact (name, phone)
Doors open | 9:00
Version / last updated
Timeline
Start | End | What happens | Where | Owner | Vendor involved | On-site contact (phone) | Notes | Status
6:30 | 7:00 | Venue access opens: keys, passes and floor plan handed over | Venue entrance | Day-of lead | Venue |  |  | Confirmed
7:00 | 8:00 | Deliveries: signage, staging, decor, printed material | Loading dock | Logistics lead | Transport |  |  | Confirmed
7:00 | 8:30 | AV load-in and set-up | Main hall | AV lead | AV company |  |  | Confirmed
7:30 | 8:15 | Catering arrives, kitchen and stations set up | Kitchen and foyer | Catering lead | Caterer |  |  | To confirm
8:00 | 8:20 | Staff and volunteer briefing | Foyer | Day-of lead |  |  |  | Confirmed
8:15 | 8:45 | Sound and slide check | Main hall | AV lead | AV company |  |  | Confirmed
8:30 | 9:00 | Registration opens | Registration desk | Registration lead |  |  |  | Confirmed
9:00 | 9:30 | Doors open, guests arrive | Main entrance | Day-of lead | Security |  |  | Confirmed
9:30 | 10:45 | Program, morning session (cues in the run of show) | Main hall | Stage manager | AV company |  |  | Confirmed
10:45 | 11:00 | Morning break | Foyer | Catering lead | Caterer |  |  | Confirmed
11:00 | 12:30 | Program, late-morning session | Main hall | Stage manager | AV company |  |  | Confirmed
12:30 | 13:30 | Lunch service | Foyer | Catering lead | Caterer |  |  | To confirm
13:30 | 15:15 | Program, afternoon session | Main hall | Stage manager | AV company |  |  | Confirmed
15:15 | 15:30 | Afternoon break | Foyer | Catering lead | Caterer |  |  | Confirmed
15:30 | 16:30 | Program, closing session | Main hall | Stage manager | AV company |  |  | Confirmed
16:30 | 17:00 | Program ends, guests leave | Main entrance | Day-of lead | Security |  |  | Confirmed
17:00 | 18:30 | Load-out: AV, decor, rentals | Main hall and loading dock | Logistics lead | AV company, Transport |  |  | To confirm
18:30 | 19:00 | Final walk-through, count of returned items | Whole venue | Day-of lead | Venue |  |  | Confirmed
19:00 | 19:30 | Venue handed back, keys returned | Venue entrance | Day-of lead | Venue |  |  | Confirmed
Vendor arrivals and departures
Vendor | Category | Arrives | Load-in point | Set up by | Departs | On-site contact | Phone | Confirmed?
Venue
AV
Catering
Security
Decor
Transport
Key contacts
Role | Name |  | Phone
Day-of lead
Venue duty manager
Security lead
First aid
AV lead
Catering lead
Transport

## How to use
How to use
This is the one-page plan for the whole day: who is where, when, and which vendor arrives at what time. It is not the cue-by-cue script of the show: that is the run of show.
Fill in the header once: event, venue, address, day-of lead, venue contact. Doors open is prefilled at 09:00 as an example: change it.
The Timeline holds about twenty sample rows for a one-day conference. Replace them with your own and sort them by start time.
Enter times as hh:mm. An End earlier than its Start turns red: this sheet does not handle a day that crosses midnight.
Set the status of each row: To confirm turns the row amber, Done grays it out and strikes it through.
Vendor arrivals and departures: one row per vendor, with the load-in point, the time it arrives, the time it must be set up by, and when it leaves.
A Set up by later than Doors open turns red: a vendor still setting up when guests walk in. Leave Doors open empty and this check stays off.
Confirm every vendor arrival the day before, then set Confirmed? to Yes. A No turns the row amber.
Key contacts: keep the numbers people will actually call on the day, and only those.
Print a dated version and share it with the team. Note the version and the update time in the header, so nobody works from an old copy.
The article that walks through the method: https://squena.com/blog/day-of-event-schedule-template?utm_source=modele-xlsx&utm_medium=fichier&utm_campaign=day-of-event-schedule-template
Template by Squena, the workspace for event organizers — squena.com