## Committee roles
Event committee roles and responsibilities
Event
Date
Committee chair
Last updated
Role | Person | Responsibilities | Decides on | Budget authority | Spending limit | Reports to | Backup | Contact
Chair |  | Leads the committee, runs the meetings, makes the final call when the committee is split | Priorities, go / no-go, tie-breaks | Approves spending |  | Committee
Vice-chair |  | Steps in for the chair, follows up on actions between meetings | Task allocation, schedule changes | View only |  | Chair
Treasurer |  | Tracks the budget, pays invoices, reports on spending at each meeting | Payment timing, budget transfers within limits | Approves spending |  | Chair
Secretary |  | Takes minutes, sends agendas, keeps contracts and documents | Meeting agendas, document filing | None |  | Chair
Venue and logistics lead |  | Venue booking, floor plan, deliveries, on-site logistics | Room layout, delivery slots | Spend up to a limit | 500 | Vice-chair
Vendor and procurement lead |  | Requests and compares quotes, is the vendors' contact until the event | Vendor shortlist | Spend up to a limit | 500 | Vice-chair
Program lead |  | Builds the agenda, briefs speakers, keeps the day to time | Session formats, running order | Spend up to a limit | 500 | Vice-chair
Marketing and communications lead |  | Website, invitations, social media, press | Messages, publication dates | Spend up to a limit | 500 | Vice-chair
Sponsorship lead |  | Finds sponsors, manages their benefits and their payments | Sponsor packages, benefits offered | View only |  | Vice-chair
Volunteer coordinator |  | Recruits, briefs and schedules volunteers | Shifts, volunteer assignments | None |  | Vice-chair
Guest experience and registration lead |  | Registration, signage, welcome, guest questions | Registration rules, welcome flow | None |  | Vice-chair
Safety and accessibility lead |  | Risk assessment, first aid, access needs, emergency plan | Safety measures, accessibility adjustments | None |  | Chair

## RACI
Who does what: RACI chart
R = does the work · A = owns the decision (one per task) · C = consulted before · I = informed after
Task | [12 empty] | A count | R count
Set the budget | A | C | R | I | C | C | C | C | C | I | I | I
Book the venue | A | C | C | I | R | C | C | I | I | I | C | C
Choose vendors | C | A | C | I | C | R | C | I | I | I | I | C
Sign contracts | A | I | C | R | C | R | C | I | I | I | I | I
Approve spending | R | C | A | I | C | C | C | C | C | I | I | I
Build the program | C | A | I | I | C | I | R | C | C | I | C | C
Marketing and communications | C | A | I | I | I | I | C | R | R | I | C | I
Volunteer schedule | I | A | I | I | C | I | I | I | I | R | C | C
Run the event day | A | C | I | I | R | C | R | I | I | R | R | R
Post-event report | A | C | C | R | C | C | C | C | C | C | C | C

## How to use
How to use
This file sets out who does what on an event committee: a table of roles, then a RACI chart.
Committee roles tab: fill in the header, then one row per role. Twelve sample roles are there, with short generic responsibilities and no names. Keep, rename or clear them (do not delete the rows: the RACI headers read them).
Put a name in Person for every role. A role with no person turns amber: it is a role nobody owns yet.
Budget authority says how far a role can go with money. Pick Spend up to a limit and you must give the Spending limit: without it the cell turns red. The 500 shown is an example, replace it.
RACI tab: the column headers come from the Committee roles tab by formula. Rename a role there and the chart follows.
Each cell takes R, A, C or I. R = does the work, A = owns the decision, C = consulted before, I = informed after.
Each task needs exactly one A. The A count turns red when it is not 1. The R count turns amber when nobody does the work.
The chart is a suggested starting point, not a rule: change every letter that does not match your committee.
Review the chart when someone joins or leaves the committee, and after every change of role.
The RACI chart reads the first twelve rows of the Committee roles table: a role added below the twelfth row does not appear on it.
The article that walks through the method: https://squena.com/blog/event-committee-roles-and-responsibilities?utm_source=modele-xlsx&utm_medium=fichier&utm_campaign=event-committee-roles-template
Template by Squena, the workspace for event organizers — squena.com