## Production schedule
Event production schedule (day-minus)
Event name
Event day | [10 empty] | Weekly Gantt — purple: upcoming · red: overdue · gray: done · ◆: milestone · dark column: event day · amber: this week
Today
Phase | Category | Task | Owner | Vendor | D-N | Duration (days) | Start | Due date | Status | Notes
Scoping | Scoping | Define the event objective | Leadership |  | 180 | 10 |  |  | To do
Scoping | Budget | Set the budget envelope | Leadership |  | 175 | 10 |  |  | To do
Scoping | Scoping | Pick the date and a backup date | Leadership |  | 170 | 7 |  |  | To do
Scoping | Venue | Shortlist venue options | Project lead |  | 160 | 14 |  |  | To do
Scoping | Scoping | Confirm the format (in-person, hybrid, virtual) | Leadership |  | 150 | 7 |  |  | To do
Scoping | Scoping | Write the event brief | Project lead |  | 130 | 14 |  |  | To do
Vendors | Venue | Write the venue brief | Project lead |  | 120 | 7 |  |  | To do
Vendors | Venue | Request venue quotes | Project lead |  | 115 | 14 |  |  | To do
Vendors | Catering | Request catering quotes | Project lead |  | 110 | 14 |  |  | To do
Vendors | Production | Request production quotes (sound, lighting, video) | Project lead |  | 105 | 14 |  |  | To do
Vendors | Security | Request security quotes | Project lead |  | 100 | 14 |  |  | To do
Vendors | Venue | Visit shortlisted venues | Project lead |  | 95 | 10 |  |  | To do
Contracts | Budget | Compare the quotes received | Project lead |  | 90 | 7 |  |  | To do
Contracts | Venue | Sign the venue contract | Leadership |  | 85 | 5 |  |  | To do
Contracts | Production | Sign the production contract | Project lead |  | 80 | 5 |  |  | To do
Contracts | Catering | Sign the catering contract | Project lead |  | 75 | 5 |  |  | To do
Contracts | Budget | Pay deposits | Admin |  | 70 | 5 |  |  | To do
Communications & team | Communications | Draft the communication plan | Communications |  | 65 | 10 |  |  | To do
Communications & team | Communications | Open registration | Communications |  | 60 | 0 |  |  | To do
Communications & team | Team | Recruit on-site staff (hosts, stage managers) | Project lead |  | 55 | 21 |  |  | To do
Logistics | Venue | Draw up the floor plan | Project lead |  | 45 | 10 |  |  | To do
Communications & team | Communications | Send registration reminders | Communications |  | 40 | 0 |  |  | To do
Logistics | Production | Write the technical rider | Stage manager |  | 35 | 10 |  |  | To do
Logistics | Admin | Check permits and licenses with your local authority | Admin |  | 30 | 10 |  |  | To do
Logistics | Security | Confirm the security plan | Project lead |  | 20 | 7 |  |  | To do
Final details | Scoping | Finalize the run sheet | Project lead |  | 10 | 7 |  |  | To do
Final details | Team | Brief the on-site team | Project lead |  | 5 | 1 |  |  | To do
Final details | Scoping | Confirm all vendors | Project lead |  | 3 | 3 |  |  | To do
Final details | Logistics | Receive deliveries | Stage manager |  | 1 | 1 |  |  | To do
Final details | Venue | Build the venue (load-in) | Stage manager |  | 1 | 1 |  |  | To do
Event day | Scoping | Open doors | Project lead |  | 0 | 0 |  |  | To do
After | Venue | Strike the venue (load-out) | Stage manager |  | -1 | 1 |  |  | To do
After | Budget | Receive invoices | Admin |  | -10 | 9 |  |  | To do
After | Budget | Pay vendors within the agreed terms | Admin |  | -20 | 10 |  |  | To do
After | Scoping | Debrief and update the vendor file for next time | Project lead |  | -30 | 10 |  |  | To do

## Timeline by type
Event planning timeline by type
Event day |  | From the Production schedule tab: enter it there.
Event type | Conference, 100 to 300 people |  |  | Pick one of the five formats: its column sets the dates.
Today
Weeks before the event day, by format (negative = after)
Milestone | Conference, 100 to 300 people | Convention, 300 to 1,500 people | Festival, several stages | Client evening, 50 to 150 people | Trade show with exhibitors | Weeks before, your type | Date | Done
Set the objective and budget | 17 | 52 | 61 | 10 | 52 |  |  | No
Book the venue | 16 | 48 | 56 | 9 | 48 |  |  | No
Open exhibitor and sponsor sales, if any | 14 | 40 | 48 |  | 44 |  |  | No
Hotel room block, if any | 14 | 40 | 44 |  | 40 |  |  | No
Send the save-the-date or invitations | 12 | 32 | 40 | 6 | 30 |  |  | No
Confirm headline speakers or acts | 12 | 30 | 36 | 5 | 26 |  |  | No
Sign the main vendors (production, catering, security) | 10 | 26 | 30 | 5 | 22 |  |  | No
Open registration, ticketing or RSVPs | 10 | 26 | 36 | 4 | 20 |  |  | No
Technical lock | 6 | 13 | 17 | 3 | 13 |  |  | No
Print deadline | 3 | 6 | 8 | 1.4 | 6 |  |  | No
Final headcount to the caterer | 1 | 2 | 2 | 1 | 2 |  |  | No
Run of show final | 1 | 2 | 2 | 1 | 2 |  |  | No
Event day | 0 | 0 | 0 | 0 | 0 |  |  | No
Debrief and close the budget | -2 | -3 | -4 | -2 | -3 |  |  | No

## How to use
How to use
This file helps you build an event's production schedule, from scoping to debrief.
Enter the event day at the top of the Production schedule tab: due dates calculate themselves.
Each row is a task: phase, category, task, owner, vendor, D-N, duration, start, due date, status, notes.
The D-N column is the number of days before the event day. A negative number places the task after the event day (for example the debrief, at D+30).
The Due date column calculates itself (event day minus D-N): don't type it by hand.
The Duration column (in days) is yours to fill in. A blank or zero duration marks a milestone (◆), with no spread.
The Start column calculates itself: it counts back from the due date by the duration you set.
The tasks and timings are ballpark figures: adjust them to your event's format.
Pick the status from the drop-down list: To do, In progress, Done, Blocked.
An overdue row (due date passed, status other than Done) turns red automatically.
A due date within 7 days that isn't handled yet turns amber.
A row with status Done shows grayed out and struck through.
To the right of the table, the Gantt chart gives each week its own column, starting on the Monday of the earliest task, across 40 weeks. Beyond that, bars run off the view.
Each bar follows its task: purple for upcoming, red for overdue, gray for done. A diamond ◆ marks a milestone.
The event day's column shows a subtle band, and the current week an amber one, even on rows with no task.
To read it all when printing, choose A3: the Gantt chart runs wide.
To add rows, copy the format of an existing row to keep the colors and formulas.
The Timeline by type tab lists the key milestones, from objective to debrief, in weeks before the event day for five formats. Pick your event type at the top: the dates follow the event day of the Production schedule tab.
The weeks are starting points, to adjust. The first milestone, technical lock and print deadline take the top of each range in the article's table (a month counted as 52/12 weeks, 10 days as 1.4 weeks); a blank means the milestone doesn't apply to that format.
A milestone turns red when its date has passed and Done isn't Yes, and amber within 14 days. A negative number of weeks places it after the event day.
The article that walks through the method: https://squena.com/blog/event-production-timeline?utm_source=modele-xlsx&utm_medium=fichier&utm_campaign=event-production-schedule-template
Template by Squena, the workspace for event organizers — squena.com